## Jan-June, 2023
CATANDUANES STATE UNIVERSITY
Procurement Monitoring Report as of June 30, 2023
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed/ Purchase Order | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
PUBLIC BIDDING (GOODS)
1 | Procurement of One (1) Year Security Services | R. Timbal | No | Public Bidding | 2023-03-02 | 2023-03-03 | 2023-03-14 |  | 2023-03-27 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2023-04-18 | 2023-04-26 | 2023-04-28 | Completed |  | GAA 2023 & SBUI 2023 | 7165744.2 |  | 7165744.2 | 7165744.2 |  | 7165744.2 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-03-06 |  | 2023-03-06 | 2023-03-06 | 2023-03-28 | -
2 | Supply,Delivery,Installation, Testing and Commissioning of High-Volume Low-Speed Industrial Ceiling Fan for CatSU Gymnasium | BH. Nuyda | No | Public Bidding | 2023-03-02 | 2023-03-17 | N/A |  | 2023-04-14 | 2023-04-14 | 2023-05-05 | 2023-05-05 | 2023-05-12 | 2023-05-20 | 2023-06-05 | Completed |  | GAA FY 2022 | 730000 |  | 730000 | 700000 |  | 700000 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | NA |  | 2023-04-14 | 2023-04-14 | 2023-05-05 | -
PUBLIC BIDDING (INFRASTRUCTURE)
1 | Construction of Main Campus Student Development Center | BH. Nuyda | No | Public Bidding | 2023-11-01 | 2023-01-17 | 2023-01-25 |  | 2023-02-08 | 2023-02-10 | 2023-02-15 | 2023-02-15 | 2023-03-16 | 2023-03-20 | 2023-03-22 | Ongoing Construction |  | GAA FY 2023 | 24750000 |  | 24750000 | 23859626.17 |  | 23859626.17 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso 4. Mr. Alexander Ang Hung | 2023-01-18 |  | 2023-01-18 | 2023-01-18 | 2023-02-10
2 | Establishment of Water Catchment Basin | BH. Nuyda | No | Public Bidding | 2023-03-08 | 2023-03-10 | 2023-03-20 |  | 2023-04-03 | 2023-04-03 | 2023-04-25 | 2023-04-25 | 2023-06-08 | 2023-06-14 | 2023-06-14 | Ongoing Construction |  | GAA FY 2023 | 14851485.15 |  | 14851485.15 | 13381728.08 |  | 13381728.08 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso 4. Mr. Alexander Ang Hung | 2023-03-06 |  | 2023-03-06 | 2023-03-06 | 2023-04-25
SHOPPING/SMALL VALUE PROCUREMENT
1 | Books | J. Perez | No | SVP | N/A | N/A | N/A |  | 2022-12-21 | 2022-12-21 | N/A | 2022-12-21 | N/A | N/A | 2023-01-05 |  |  | 164 | 49760 | 49760 |  | 25055 | 25055
2 | Books | I. Aranel | No | SVP | N/A | 2022-11-12 | N/A |  | 2022-12-21 | 2022-12-21 | N/A | 2022-12-21 | N/A | N/A | 2023-01-05 |  |  | 101 | 74823 | 74823 |  | 50390 | 50390
3 | Books | I. Aranel | No | SVP | N/A | 2022-11-11 | N/A |  | 2022-12-21 | 2022-12-21 | N/A | 2022-12-21 | N/A | N/A | 2023-01-05 |  |  | 164 | 169235.85 | 169235.85 |  | 74114 | 74114
4 | Books | P. Arcilla | No | SVP | N/A | 2022-07-20 | N/A |  | 2022-12-21 | 2022-12-21 | N/A | 2022-12-21 | N/A | N/A | 2023-01-05 |  |  | 164 | 50335 | 50335 |  | 10288 | 10288
5 | IT Equipment & Supplies | J. Masagca | No | SVP | N/A | 2022-12-05 | N/A |  | 2022-12-14 | 2022-12-14 | N/A | 2022-12-14 | N/A | N/A | 2023-01-05 |  |  | SP | 651626.8 | 651626.8 |  | 563505 | 563505
6 | Meals & Snacks | J. Salvador | No | SVP | N/A | N/A | N/A |  | 2022-12-21 | 2022-12-21 | N/A | 2022-12-21 | N/A | N/A | 2023-01-05 |  |  | 164 | 14400 | 14400 |  | 12400 | 12400
7 | Other Supplies & Materials | J. Masagca | No | SVP | N/A | 2022-10-21 | N/A |  | 2023-12-28 | 2023-12-28 | N/A | 2023-12-28 | N/A | N/A | 2023-01-05 |  |  | 164 | 53000 | 53000 |  | 53000 | 53000
8 | Glass Materials | E. Pante | No | SVP | N/A | N/A | N/A |  | 2023-12-28 | 2023-12-28 | N/A | 2023-12-28 | N/A | N/A | 2023-01-05 |  |  | 164 | 5600 | 5600 |  | 5460 | 5460
9 | Snacks | M. Tejada | No | SVP | N/A | N/A | N/A |  | 2023-12-28 | 2023-12-28 | N/A | 2023-12-28 | N/A | N/A | 2023-01-05 |  |  | 164 | 7200 | 7200 |  | 7200 | 7200
10 | Glass Materials | L. Custodio | No | SVP | N/A | N/A | N/A |  | 2023-01-06 | 2023-01-06 | N/A | 2023-01-06 | N/A | N/A | 2023-01-10 |  |  | 164 | 11644 | 11644 |  | 11644 | 11644
11 | Oil & Lubricants | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-01-06 | 2023-01-06 | N/A | 2023-01-06 | N/A | N/A | 2023-01-10 |  |  | 101 | 3900 | 3900 |  | 3800 | 3800
12 | Oil & Lubricants | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-01-06 | 2023-01-06 | N/A | 2023-01-06 | N/A | N/A | 2023-01-10 |  |  | 101 | 11400 | 11400 |  | 11400 | 11400
13 | Meals & Snacks | L. Custodio | No | SVP | N/A | N/A | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 101 | 30400 | 30400 |  | 28800 | 28800
14 | Oil & Lubricants | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 164 | 4500 | 4500 |  | 3780 | 3780
15 | Upholstery Services | J. Tria | No | SVP | N/A | N/A | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 164 | 4000 | 4000 |  | 4000 | 4000
16 | Office Equipment | AP. Laynes | No | SVP | N/A |  | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 164 | 85000 | 85000 |  | 85000 | 85000
17 | Oil & Lubricants | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 164 | 11307 | 11307 |  | 9441 | 9441
18 | Food Stuff | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2023-01-11 | 2023-01-11 | N/A | 2023-01-11 | N/A | N/A | 2023-01-13 |  |  | 163 | 40800 | 40800 |  | 40800 | 40800
19 | Office Supplies | J. Tria | No | Shopping | N/A | 2023-01-18 | N/A |  | 2023-01-18 | 2023-01-18 | N/A | 2023-01-18 | N/A | N/A | 2023-01-24 |  |  | 164 | 529296.18 | 529296.18 |  | 432157.5 | 432157.5
20 | Tarpaulin Printing | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-01-18 | 2023-01-18 | N/A | 2023-01-18 | N/A | N/A | 2023-01-24 |  |  | 164 | 8448 | 8448 |  | 8192 | 8192
21 | Tarpaulin Printing | E. Lanon | No | SVP | N/A | N/A | N/A |  | 2023-01-18 | 2023-01-18 | N/A | 2023-01-18 | N/A | N/A | 2023-01-24 |  |  | 164 | 1200 | 1200 |  | 1200 | 1200
22 | Snacks | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2023-01-02 | N/A | N/A | 2/13/2023 |  |  | 164 | 14850 | 14850 |  | 14850 | 14850
23 | Bookbinding | R. Samonte/ MC. Tuldac | No | SVP | N/A | N/A | N/A |  | 1/25/2023 | 1/25/2023 | N/A | 1/25/2023 | N/A | N/A | 2/13/2023 |  |  | 164 | 1750 | 1750 |  | 1740 | 1740
24 | Office supplies | R. Samonte/ MC. Tuldac | No | Shopping | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 2/13/2023 |  |  | 164 | 2036 | 2036 |  | 1726.5 | 1726.5
25 | Accommodation | J. Masagca | No | SVP | N/A | 10/6/2022 | N/A |  | 1/25/2023 | 1/25/2023 | N/A | 1/25/2023 | N/A | N/A | 2/13/2023 |  |  | SP | 115000 | 115000 |  | 115000 | 115000
26 | Fishery supplies | MJ. Ramos | No | SVP | N/A | 1/18/2023 | N/A |  | 1/25/2023 | 1/25/2023 | N/A | 1/25/2023 | N/A | N/A | 2/13/2023 |  |  | 164 | 210534 | 210534 |  | 210096 | 210096
27 | Tarpaulin Printing | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 2/13/2023 |  |  | SP | 3780 | 3780 |  | 2700 | 2700
28 | Tarpaulin Printing | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 2/13/2023 |  |  | SP | 1680 | 1680 |  | 1200 | 1200
29 | Tarpaulin Printing | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 213/2023 |  |  | SP | 1680 | 1680 |  | 1200 | 1200
30 | Tarpaulin Printing | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 2/13/2023 |  |  | SP | 2240 | 2240 |  | 2240 | 2240
31 | IT peripherals | E. Millon | No | Shopping | N/A | N/A | N/A |  | 2/1/2023 | 2/1/2023 | N/A | 2/1/2023 | N/A | N/A | 2/13/2023 |  |  | 101 | 8495 | 8495 |  | 8495 | 8495
32 | Other Supplies & Materials | L. Sicio | No | SVP | N/A | N/A | N/A |  | 1/25/2023 | 1/25/2023 | N/A | 1/25/2023 | N/A | N/A | 2/13/2023 |  |  | 101 | 49500 | 49500 |  | 49350 | 49350
33 | Hardware Materials | BH. Nuyda | No | SVP | N/A | 11/7/2022 | N/A |  | 2/8/2023 | 2/8/2023 | N/A | 2/8/2023 | N/A | N/A | 2/14/2023 |  |  | 101 | 63092 | 63092 |  | 62891 | 62891
34 | Office Supplies | RF. Sarmiento | No | Shopping | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 101 | 2805 | 2805 |  | 2785 | 2785
35 | Snacks | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 101 | 3750 | 3750 |  | 3750 | 3750
36 | Snacks | M. Tejada | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 164 | 6100 | 6100 |  | 6100 | 6100
37 | Office Furniture & Fixtures | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 101 | 3735 | 3735 |  | 1357 | 1357
38 | Poultry Supplies | G. Samas | No | SVP | N/A | 2023-02-06 | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 163 | 62990 | 62990 |  | 59000 | 59000
39 | Electrical Materials | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 101 | 42350 | 42350 |  | 42180 | 42180
40 | Meals & Snacks | J. Rojas | No | SVP | N/A | 2023-01-18 | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 101 | 120000 | 120000 |  | 120000 | 120000
41 | Other Supplies | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 163 | 12150 | 12150 |  | 11535 | 11535
42 | Agricultural Supplies | C. Mejes | No | SVP | N/A | 2023-02-06 | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-02-28 |  |  | 163 | 98920 | 98920 |  | 60060 | 60060
43 | Snacks | ME. Iñigo | No | SVP | N/A | N/A | N/A |  | 2023-02-22 | 2023-02-22 | N/A | 2023-02-22 | N/A | N/A | 2023-03-02 |  |  | 101 | 18000 | 18000 |  | 18000 | 18000
44 | Office Supplies | E. Somido | No | Shopping | N/A | 2023-02-27 | N/A |  | 2023-03-01 | 2023-03-01 | N/A | 2023-03-01 | N/A | N/A | 2023-03-09 |  |  | 163 | 205000 | 205000 |  | 126250 | 126250
45 | Other Supplies | E. Somido | No | SVP | N/A | N/A | N/A |  | 2023-03-01 | 2023-03-01 | N/A | 2023-03-01 | N/A | N/A | 2023-03-09 |  |  | 163 | 7500 | 7500 |  | 7000 | 7000
46 | Office Equipment | G. Acedo | No | SVP | N/A | 2023-03-06 | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 101 | 70000 | 70000 |  | 48760 | 48760
47 | Tarpaulin Printing | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 101 | 1540 | 1540 |  | 1540 | 1540
48 | Layer Mash | E. Somido | No | SVP | N/A | 2023-02-17 | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 163 | 378000 | 378000 |  | 376950 | 376950
49 | Hardware Materials | G. Acedo | No | SVP | N/A | 2023-03-06 | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 101 | 66144 | 66144 |  | 66144 | 66144
50 | Janitorial Supplies | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 101 | 8080 | 8080 |  | 7951 | 7951
51 | Office Supplies | G. Acedo | No | Shopping | N/A | N/A | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 101 | 13415.4 | 13415.4 |  | 13105 | 13105
52 | Agricultural Supplies | A. Manalo | No | SVP | N/A | 2023-02-17 | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-03-20 |  |  | 163 | 151400 | 151400 |  | 150076 | 150076
53 | Snacks | ZM. Tumala | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 7000 | 7000 |  | 7000 | 7000
54 | Snacks | R. Santelices | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 7000 | 7000 |  | 7000 | 7000
55 | Snacks | ME. Iñigo | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 7000 | 7000 |  | 7000 | 7000
56 | Snacks | ME. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 24200 | 24200 |  | 24200 | 24200
57 | Snacks | R. Santelices | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 10000 | 10000 |  | 10000 | 10000
58 | Meals | ZM. Tumala | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-24 |  |  | 101 | 2800 | 2800 |  | 2800 | 2800
59 | Vehicle Spareparts | KK. Araojo | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-29 |  |  | 164 | 21000 | 21000 |  | 19960 | 19960
60 | Fuel | KK. Araojo | No | SVP | N/A | 2023-03-13 | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-29 |  |  | 101 | 600000 | 600000 |  | 436257.6 | 436257.6
61 | Hardware Materials | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 42705 | 42705 |  | 39635 | 39635
62 | Snacks | R. Santelices | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 7000 | 7000 |  | 7000 | 7000
63 | Other Supplies | JW. Dianela | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 49500 | 49500 |  | 49350 | 49350
64 | Hardware Materials | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 5750 | 5750 |  | 5575.5 | 5575.5
65 | Hardware Materials | E. Romero | No | SVP | N/A | 2023-03-13 | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 89860 | 89860 |  | 79650 | 79650
66 | IT Supplies | M. Cariaso | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 2800 | 2800 |  | 2200 | 2200
67 | Kitchenwares | E. Rojas | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 2040 | 2040 |  | 2015 | 2015
68 | IT Supplies | E. Rojas | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 18000 | 18000 |  | 10800 | 10800
69 | Medical Supplies | F. Ma | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 42090 | 42090 |  | 41365 | 41365
70 | Hardware Materials | E. Romero | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 24959 | 24959 |  | 21598 | 21598
71 | Snacks | MS. Gregorio | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 164 | 6800 | 6800 |  | 6800 | 6800
72 | IT Supplies | M. Tejada | No | Shopping | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 101 | 7500 | 7500 |  | 7405 | 7405
73 | IT Equipment | R. Lizaso | No | SVP | N/A | 2023-03-10 | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | 164 | 52500 | 52500 |  | 51490 | 51490
74 | Van Rental | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | SP | 19500 | 19500 |  | 19500 | 19500
75 | Office Supplies | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-03-31 |  |  | SP | 10500 | 10500 |  | 10425 | 10425
76 | Vehicle Spareparts | KK. Araojo | No | SVP | N/A | 2023-02-27 | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-04-04 |  |  | 101 | 99621.5 | 99621.5 |  | 98160 | 98160
77 | Vehicle Spareparts | KK. Araojo | No | SVP | N/A | N/A | N/A |  | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | N/A | 2023-04-04 |  |  | 101 | 46744 | 46744 |  | 46060 | 46060
78 | Other Supplies | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 27300 | 27300 |  | 25734 | 25734
79 | Smoke Detector | BH. Nuyda | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 9900 | 9900 |  | 9900 | 9900
80 | Supply, Delivery & Installation & Aluminum Screen Detector | BH. Nuyda | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 5940 | 5940 |  | 5712 | 5712
81 | Tarpaulin Printing Services | R. Torres | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 3500 | 3500 |  | 3049 | 3049
82 | Hardware Materials | P. Arcilla | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 25000 | 25000 |  | 20655 | 20655
83 | Office & IT Supplies | ME. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 13354 | 13354 |  | 11713 | 11713
84 | Meals & Snacks | E. Pante | No | SVP | N/A | 2023-03-13 | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 164400 | 164400 |  | 151800 | 151800
85 | Snacks | D. Toyado | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 15000 | 15000 |  | 15000 | 15000
86 | Office Supplies | J. Resayaga | No | Shopping | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 164 | 2580 | 2580 |  | 2395 | 2395
87 | Snacks | J. Tria | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 30800 | 30800 |  | 30800 | 30800
88 | Vehicle Supplies | E. Romero | No | SVP | N/A | 2023-03-10 | N/A |  | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | N/A | N/A | 2023-04-04 |  |  | 101 | 99600 | 99600 |  | 97990 | 97990
89 | Snacks | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 4000 | 4000 |  | 4000 | 4000
90 | Meals & Snacks | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 39000 | 39000 |  | 39000 | 39000
91 | Snacks | ME. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 101 | 2000 | 2000 |  | 2000 | 2000
92 | Office Supplies | MS. Gregorio | No | Shopping | N/A | N/A | N/A |  | 2023-03-21 | 2023-03-21 | N/A | 2023-03-21 | N/A | N/A | 2023-04-04 |  |  | 164 | 9225 | 9225 |  | 7240 | 7240
93 | Vehicle Spareparts | KK. Araojo | No | SVP | N/A | N/A | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 101 | 23000 | 23000 |  | 22900 | 22900
94 | Snacks | E. Lanon | No | SVP | N/A | N/A | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 164 | 25000 | 25000 |  | 25000 | 25000
95 | Vehicle Spareparts | Z. Reyes | No | SVP | N/A | 2023-03-24 | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 101 | 67900 | 67900 |  | 67580 | 67580
96 | IT Supplies | Z. Reyes | No | SVP | N/A | 2023-03-24 | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 101 | 97300 | 97300 |  | 79945 | 79945
97 | Hardware Materials | Z. Reyes | No | SVP | N/A | 2023-03-24 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 135050 | 135050 |  | 122170 | 122170
98 | Office Equipment | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 15000 | 15000 |  | 14394 | 14394
99 | Snacks | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 10500 | 10500 |  | 10500 | 10500
100 | Furniture & Fixtures | M. Cariaso | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 5000 | 5000 |  | 4899 | 4899
101 | Snacks | M. Cariaso | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 660 | 660 |  | 660 | 660
102 | Furniture & Fixtures | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 36000 | 36000 |  | 35498 | 35498
103 | Sala Set | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 30000 | 30000 |  | 28899 | 28899
104 | Medical Supplies | Z. Reyes | No | SVP | N/A | 2023-03-20 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 74560 | 74560 |  | 73286 | 73286
105 | Fuel, Oil & Lubricants | Z. Reyes | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 196750 | 196750 |  | 158841 | 158841
106 | Other Supplies | M. Tejada | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 164 | 525000 | 525000 |  | 374820 | 374820
107 | Snacks | G. Arcilla | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 15000 | 15000 |  | 15000 | 15000
108 | Other Supplies | M. Tejada | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 164 | 420000 | 420000 |  | 269850 | 269850
109 | Other Supplies | M. Tejada | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 164 | 90800 | 90800 |  | 46115 | 46115
110 | Other Supplies | M. Tejada | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 164 | 330000 | 330000 |  | 170100 | 170100
111 | Other Supplies | M. Tejada | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 164 | 15000 | 15000 |  | 12000 | 12000
112 | Medical Supplies | F. Ma | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 36650 | 36650 |  | 36140 | 36140
113 | Medical Supplies | F. Ma | No | SVP | N/A | N/A | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 101 | 23620 | 23620 |  | 23442 | 23442
114 | Hardware Materials | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 39850 | 39850 |  | 36890 | 36890
115 | Snacks | E. Pante | No | SVP | N/A | N/A | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 7500 | 7500 |  | 7500 | 7500
116 | Software Subscription | ME. Abundo | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 89395.2 | 89395.2 |  | 89310 | 89310
117 | Office Equipment | BH. Nuyda | No | SVP | N/A | 2023-03-17 | N/A |  | 2023-03-29 | 2023-03-29 | N/A | 2023-03-29 | N/A | N/A | 2023-04-18 |  |  | 101 | 96000 | 96000 |  | 78000 | 78000
118 | Other Supplies | BH. Nuyda | No | SVP | N/A | 2023-03-27 | N/A |  | 2023-03-30 | 2023-03-30 | N/A | 2023-03-30 | N/A | N/A | 2023-04-18 |  |  | 164 | 63750 | 63750 |  | 63000 | 63000
119 | Agricultural Supplies | J. Ramos | No | SVP | N/A | 2023-03-24 | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 37380 | 37380 |  | 37380 | 37380
120 | Electrical Materials & Office Furniture | R. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 9500 | 9500 |  | 7900 | 7900
121 | Other Supplies | E. Rojas | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 7200 | 7200 |  | 7128 | 7128
122 | Office Equipment | E. Somido | No | SVP | N/A | 2023-03-10 | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 163 | 126000 | 126000 |  | 118000 | 118000
123 | Hardware Materials | R. Torres | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 10895 | 10895 |  | 9353 | 9353
124 | Snacks | J. Olfindo | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 3400 | 3400 |  | 3400 | 3400
125 | Office Equipment | R. Lizaso | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 35000 | 35000 |  | 29800 | 29800
126 | Hardware Materials | R. Lizaso | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 7000 | 7000 |  | 2800 | 2800
127 | Meals & Snacks | MS. Gregorio | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 20250 | 20250 |  | 20250 | 20250
128 | Office Supplies | MS. Gregorio | No | Shopping | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 2400 | 2400 |  | 1639 | 1639
129 | Hardware Materials & Other Supplies | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 44280 | 44280 |  | 43850 | 43850
130 | Fuel, Oil & Lubricants | BH. Nuyda | No | SVP | N/A | 2023-03-31 | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 149070 | 149070 |  | 126023 | 126023
131 | Snacks | E. Pante | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 2500 | 2500 |  | 2500 | 2500
132 | Snacks | E. Pante | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 7500 | 7500 |  | 7000 | 7000
133 | Tarpaulin Printing Services | K. Aldea | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 1300 | 1300 |  | 589 | 589
134 | Room Accommodation | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 16250 | 16250 |  | 16250 | 16250
135 | Printing Services | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 101 | 3358 | 3358 |  | 2774 | 2774
136 | IT Supplies | A. Malijan | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-04-25 |  |  | 101 | 43800 | 43800 |  | 41100 | 41100
137 | Snacks | J. Floranza | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-04-25 |  |  | 101 | 2000 | 2000 |  | 1500 | 1500
138 | Chest Freezer | J. Aquino | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 163 | 30000 | 30000 |  | 18500 | 18500
139 | Agricultural Supplies | J. Aquino | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 30050 | 30050 |  | 18106 | 18106
140 | Meals & Snacks | G. Angeles | No | SVP | N/A | N/A | N/A |  | 2023-04-14 | 2023-04-14 | N/A | 2023-04-14 | N/A | N/A | 2023-04-25 |  |  | 164 | 17500 | 17500 |  | 15000 | 15000
141 | IT Supplies | L. Custodio | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 2255 | 2255 |  | 2000 | 2000
142 | Printing Services | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 1360 | 1360 |  | 1140 | 1140
143 | Hardware Materials | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 1110 | 1110 |  | 978 | 978
144 | Snacks | L. Custodio | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 164 | 13440 | 13440 |  | 13440 | 13440
145 | Venue Rental | MS. Gregorio | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 12750 | 12750 |  | 12750 | 12750
146 | Publication Fee | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 3300 | 3300 |  | 2500 | 2500
147 | Office Furniture & Fixtures | J. Perez | No | SVP | N/A | 2023-04-24 | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 164 | 106400 | 106400 |  | 106400 | 106400
148 | Meals & Snacks | J. Rojas | No | SVP | N/A | 2023-04-18 | N/A |  | 2023-04-25 | 2023-04-25 | N/A | 2023-04-25 | N/A | N/A | 2023-05-05 |  |  | 101 | 120000 | 120000 |  | 120000 | 120000
149 | Office Equipment | J. Perez | No | SVP | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 164 | 6150 | 6150 |  | 5565 | 5565
150 | Office Furniture & Fixtures | J. Rojas | No | SVP | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 101 | 13000 | 13000 |  | 9950 | 9950
151 | Electrical & Hardware Materials | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 101 | 44522 | 44522 |  | 40000 | 40000
152 | Other Supplies | RF. Sarmiento | No | SVP | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 101 | 3330 | 3330 |  | 3312 | 3312
153 | IT Supplies | J. Rojas | No | Shopping | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 164 | 4000 | 4000 |  | 3920 | 3920
154 | Office Supplies | E. Somido | No | Shopping | N/A | N/A | N/A |  | 2023-04-26 | 2023-04-26 | N/A | 2023-04-26 | N/A | N/A | 2023-05-05 |  |  | 163 | 26008 | 26008 |  | 24144 | 24144
155 | Office Supplies | G. Acedo | No | Shopping | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 3278.5 | 3278.5 |  | 2626 | 2626
156 | IT Supplies | P. Arcilla | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 4369 | 4369 |  | 4300 | 4300
157 | Meals & Snacks | R. Timbal | No | SVP | N/A | N/A | N/A |  | 2023-04-25 | 2023-04-25 | N/A | 2023-04-25 | N/A | N/A | 2023-05-05 |  |  | 101 | 13500 | 13500 |  | 13500 | 13500
158 | Meals & Snacks | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-05 |  |  | 101 | 20000 | 20000 |  | 15750 | 15750
159 | Hardware Materials | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 5750 | 5750 |  | 5721 | 5721
160 | Office Supplies | M. Tejada | No | Shopping | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 2250 | 2250 |  | 2242 | 2242
161 | Office Supplies | M. Tejada | No | Shopping | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 32030 | 32030 |  | 31320 | 31320
162 | Other Supplies | R. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 640 | 640 |  | 632 | 632
163 | Hardware Materials | J. Perez | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 5383 | 5383 |  | 5207 | 5207
164 | Sand | BH. Nuyda | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 7420 | 7420 |  | 7000 | 7000
165 | Other Supplies | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 21000 | 21000 |  | 15750 | 15750
166 | IT Equipment | M. Tejada | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 35000 | 35000 |  | 33995 | 33995
167 | Fuel, Oil & Lubricants | J. Ramos | No | SVP | N/A | 2023-04-26 | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 53910 | 53910 |  | 49890 | 49890
168 | Office Equipment | I. Aranel | No | SVP | N/A | 2023-04-26 | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 123000 | 123000 |  | 117677 | 117677
169 | IT Equipment | M. Cariaso | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 4500 | 4500 |  | 1895 | 1895
170 | Snacks | G. Acedo | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 12750 | 12750 |  | 12750 | 12750
171 | Snacks | J. Olfindo | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 31600 | 31600 |  | 31600 | 31600
172 | Vehicle Spareparts | AN. Rubio | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 30044 | 30044 |  | 29700 | 29700
173 | Office Furniture | M. Tejada | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 17000 | 17000 |  | 17000 | 17000
174 | Office Furniture | M. Tejada | No | SVP | N/A | 2023-04-26 | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 91000 | 91000 |  | 78000 | 78000
175 | Hardware Materials | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 101 | 5888 | 5888 |  | 5829 | 5829
176 | Other Supplies | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-05-03 | 2023-05-03 | N/A | 2023-05-03 | N/A | N/A | 2023-05-09 |  |  | 164 | 39200 | 39200 |  | 29400 | 29400
177 | Snacks | R. Khan | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-16 |  |  | 101 | 3300 | 3300 |  | 3300 | 3300
178 | Printing Services | R. Khan | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-16 |  |  | 101 | 1120 | 1120 |  | 1056 | 1056
179 | Other Supplies | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-16 |  |  | 101 | 1500 | 1500 |  | 1300 | 1300
180 | Office & IT Supplies | R. Khan | No | Shopping | N/A | N/A | N/A |  | 2023-04-19 | 2023-04-19 | N/A | 2023-04-19 | N/A | N/A | 2023-05-16 |  |  | 101 | 3414 | 3414 |  | 3079 | 3079
181 | Meals & Snacks | M. Abichuela | No | SVP | N/A | 2023-04-19 | N/A |  | 2023-04-25 | 2023-04-25 | N/A | 2023-04-25 | N/A | N/A | 2023-05-16 |  |  | 101 | 53250 | 53250 |  | 44450 | 44450
182 | Poultry Supplies | E. Somido | No | SVP | N/A | 2023-04-28 | N/A |  | 2023-04-25 | 2023-04-25 | N/A | 2023-04-25 | N/A | N/A | 2023-05-16 |  |  | 163 | 324000 | 324000 |  | 324000 | 324000
183 | Office Supplies | RF. Sarmiento | No | Shopping | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 7856 | 7856 |  | 7854 | 7854
184 | Meals & Snacks | R. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 2400 | 2400 |  | 2399 | 2399
185 | Other Supplies | I. Aranel | No | Shopping | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 2200 | 2200 |  | 2100 | 2100
186 | Meals & Snacks | J. Tonio | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 164 | 18000 | 18000 |  | 17960 | 17960
187 | Tarpaulin Printing Services | R. Abundo | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 1000 | 1000 |  | 608 | 608
188 | Office Supplies | R. Abundo | No | Shopping | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 910 | 910 |  | 904 | 904
189 | Snacks | JC. Francis | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 164 | 9450 | 9450 |  | 9450 | 9450
190 | Snacks | J.Tria | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 164 | 2450 | 2450 |  | 2450 | 2450
191 | Tarpaulin Printing Services | M. Abichuela | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 101 | 5280 | 5280 |  | 3040 | 3040
192 | IT Equipment | J. Perez | No | SVP | N/A | 2023-04-24 | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-16 |  |  | 164 | 200000 | 200000 |  | 198540 | 198540
193 | Meals & Snacks | Z. Reyes | No | SVP | N/A | N/A | N/A |  | 2023-05-17 | 2023-05-17 | N/A | 2023-05-17 | N/A | N/A | 2023-05-23 |  |  | 101 | 16000 | 16000 |  | 14960 | 14960
194 | Tarpaulin Printing Services | J. Tonio | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-23 |  |  | 164 | 1080 | 1080 |  | 608 | 608
195 | Hardware Materials | J. Ramos | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-23 |  |  | 101 | 35700 | 35700 |  | 34846 | 34846
196 | Poultry Supplies | E. Somido | No | SVP | N/A | 2023-04-28 | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-23 |  |  | 163 | 93000 | 93000 |  | 92985 | 92985
197 | Office Supplies | J. Tonio | No | Shopping | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-23 |  |  | 164 | 1563 | 1563 |  | 1560 | 1560
198 | Laboratory Equipment | R. Torres | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-05-29 |  |  | 164 | 43200 | 43200 |  | 35100 | 35100
199 | Snacks | P. Arcilla | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-05-29 |  |  | 101 | 6450 | 6450 |  | 6450 | 6450
200 | Hotel Accommodation | I. Aranel | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-05-29 |  |  | 101 | 21000 | 21000 |  | 17655 | 17655
201 | Meals & Snacks | J. Ramos | No | SVP | N/A | 2023-05-10 | N/A |  | 2023-05-15 | 2023-05-15 | N/A | 2023-05-15 | N/A | N/A | 2023-05-29 |  |  | 101 | 67500 | 67500 |  | 57750 | 57750
202 | Snacks | D. Toyado | No | SVP | N/A | N/A | N/A |  | 2023-05-10 | 2023-05-10 | N/A | 2023-05-10 | N/A | N/A | 2023-05-29 |  |  | 101 | 9900 | 9900 |  | 9900 | 9900
203 | Snacks | G. Angeles | No | SVP | N/A | N/A | N/A |  | 2023-05-17 | 2023-05-17 | N/A | 2023-05-17 | N/A | N/A | 2023-05-31 |  |  | 164 | 39750 | 39750 |  | 39750 | 39750
204 | Hardware Materials | R. Lizaso | No | SVP | N/A | N/A | N/A |  | 2023-06-01 | 2023-06-01 | N/A | 2023-06-01 | N/A | N/A | 2023-06-14 |  |  | 164 | 16990 | 16990 |  | 16953 | 16953
205 | Meals & Snacks | D. Manlangit | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-14 |  |  | 101 | 30000 | 30000 |  | 30000 | 30000
206 | Other Supplies | D. Manlangit | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-14 |  |  | 101 | 45000 | 45000 |  | 42750 | 42750
207 | Electronic Equipment | J. Olfindo | No | SVP | N/A | 2023-04-26 | N/A |  | 2023-06-14 | 2023-06-14 | N/A | 2023-06-14 | N/A | N/A | 2023-06-20 |  |  | 101 | 273900 | 273900 |  | 249998 | 249998
208 | Snacks | ZM. Tumala | No | SVP | N/A | N/A | N/A |  | 2023-06-14 | 2023-06-14 | N/A | 2023-06-14 | N/A | N/A | 2023-06-20 |  |  | 101 | 9000 | 9000 |  | 9000 | 9000
209 | Snacks | J. Tria | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-20 |  |  | 164 | 13160 | 13160 |  | 13160 | 13160
210 | Aquarium & Supplies | J. Masagca | No | SVP | N/A | 2023-05-12 | N/A |  | 2023-06-01 | 2023-06-01 | N/A | 2023-06-01 | N/A | N/A | 2023-06-20 |  |  | SP | 56400 | 56400 |  | 49360 | 49360
211 | Office Equipment | E. Pante | No | SVP | N/A | N/A | N/A |  | 2023-06-08 | 2023-06-08 | N/A | 2023-06-08 | N/A | N/A | 2023-06-20 |  |  | 164 | 4800 | 4800 |  | 4200 | 4200
212 | Other Supplies | J. Ramos | No | SVP | N/A | 2023-05-12 | N/A |  | 2023-06-08 | 2023-06-08 | N/A | 2023-06-08 | N/A | N/A | 2023-06-20 |  |  | 164 | 76000 | 76000 |  | 62500 | 62500
213 | IT Equipment | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2023-06-08 | 2023-06-08 | N/A | 2023-06-08 | N/A | N/A | 2023-06-20 |  |  | SP | 33600 | 33600 |  | 32040 | 32040
214 | Bamboo | J. Masagca | No | SVP | N/A | 2023-05-12 | N/A |  | 2023-06-08 | 2023-06-08 | N/A | 2023-06-08 | N/A | N/A | 2023-06-20 |  |  | SP | 50000 | 50000 |  | 47250 | 47250
215 | Office Supplies | D. Manlangit | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-20 |  |  | 101 | 29475 | 29475 |  | 28637.5 | 28637.5
216 | Snacks | L. Custodio | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-20 |  |  | 164 | 7500 | 7500 |  | 7500 | 7500
217 | Furniture & Fixtures | A. Malijan | No | SVP | N/A | N/A | N/A |  | 2023-05-17 | 2023-05-17 | N/A | 2023-05-17 | N/A | N/A | 2023-06-20 |  |  | 101 | 25500 | 25500 |  | 25350 | 25350
218 | Tarpaulin Printing Services | J. Masagca | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-20 |  |  | SP | 35000 | 35000 |  | 19380 | 19380
219 | Other Supplies | J. Floranza | No | SVP | N/A | N/A | N/A |  | 2023-06-08 | 2023-06-08 | N/A | 2023-06-08 | N/A | N/A | 2023-06-20 |  |  | 164 | 24200 | 24200 |  | 20619 | 20619
220 | Printing Materials | J. Floranza | No | SVP | N/A | N/A | N/A |  | 2023-06-14 | 2023-06-14 | N/A | 2023-06-14 | N/A | N/A | 2023-06-20 |  |  | 164 | 17050 | 17050 |  | 16895 | 16895
221 | Other Supplies | J. Floranza | No | SVP | N/A | 2023-06-01 | N/A |  | 2023-06-14 | 2023-06-14 | N/A | 2023-06-14 | N/A | N/A | 2023-06-20 |  |  | 164 | 100300 | 100300 |  | 52905 | 52905
222 | Tarpaulin Printing Services | MS. Gregorio | No | SVP | N/A | N/A | N/A |  | 2023-05-24 | 2023-05-24 | N/A | 2023-05-24 | N/A | N/A | 2023-06-20 |  |  | 164 | 6400 | 6400 |  | 4294 | 4294
223 | Tarpaulin Printing Services | J. Floranza | No | SVP | N/A | N/A | N/A |  | 2023-06-14 | 2023-06-14 | N/A | 2023-06-14 | N/A | N/A | 2023-06-27 |  |  | 164 | 8900 | 8900 |  | 8500 | 8500
AGENCY TO AGENCY
1 | Postage Stamp |  | No | Agency to Agency | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 25000 | 25000 |  | 25000 | 25000
DIRECT CONTRACTING
1 | Photocopier Supplies & Materials |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 58040.64 | 58040.64 |  | 58040.64 | 58040.64
2 | Photocopier Supplies & Materials |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 21220.24 | 21220.24 |  | 21220.24 | 21220.24
3 | Photocopier Supplies & Materials |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 81312 | 81312 |  | 81312 | 81312
4 | Internet Service Upgrade |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 60000 | 60000 |  | 60000 | 60000
5 | Photocopier Supplies & Materials |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 101 | 40533.36 | 40533.36 |  | 40533.36 | 40533.36
6 | Photocopier Supplies & Materials |  | No | Direct Contracting | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 164 | 16125 | 16125 |  | 16125 | 16125
[18 empty] | Total Alloted Budget of Procurement Activities | 58849825.02 | 11352595.67 | 47497229.35
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 54816031.29 | 9708932.84 | 45107098.45
[18 empty] | Total Savings (Total Alloted Budget - Total Contract Price) | 4033793.73
ONGOING PROCUREMENT ACTIVITIES
PUBLIC BIDDING (GOODS)
1 | Procurement of Medical Laboratory Equipment for Nursing and Allied Health Programs | J. Olfindo | No | Public Bidding | 2023-03-09 | 2023-03-13 | 2023-03-22 |  | 2023-04-03 | 2023-04-03 | 2023-06-02 | 2023-06-02 | 2023-06-16 | - | - | - | - | GAA FY 2022 | 14450000 |  | 14450000 | 4247000 |  | 4247000 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-03-06 |  | 2023-03-06 | 2023-03-06 | 2023-03-06 | - | Item Nos. 3, 6, 8, 9, 12, 15, 17
[13 empty] | 2023-06-19 | 2023-06-29 | - | - | - |  |  |  |  | 2103000 |  | 2103000 | [6 empty] | - | Item Nos. 2, 4, 16, 18
[13 empty] | 2023-06-19 | 2023-07-07 | - | - | - |  |  |  |  | 2467174 |  | 2467174 | [6 empty] | - | Item Nos. 1, 5, 7, 10, 11, 13, 14, 19
2 | Procurement of Hardware Materials & Equipment for the Installation of Three Units 33KVA Distribution Transformer for Buildings: CBA, CICT, Main Library, CAS A, CAS B, Admin. Building | BH. Nuyda | No | Public Bidding | 2023-03-02 | 2023-05-02 | 2023-05-10 |  | 2023-05-22 | 2023-05-29 | 2023-06-14 | 2023-06-14 | 2023-06-22 | - | - | - | - | GAA FY 2022 | 2944781.5 |  | 2944781.5 | 2693132.95 |  | 2693132.95 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-04 |  | 2023-05-04 | 2023-05-04 | 2023-06-14 | -
3 | Procurement of Four (4) Units Mini Bus | KK. Araojo | No | Public Bidding | 2023-05-03 | 2023-05-09 | 2023-05-17 |  | 2023-05-30 | 2023-05-30 | 2023-06-14 | 2023-06-14 | - | - | - | - | - | SBUI FY 2023 | 18000000 |  | 18000000 | 18000000 |  | 18000000 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-10 |  | 2023-05-30 | 2023-05-30 | 2023-06-05 | -
4 | Procurement of Sports Utility Vehicle & Motorcycle (Lot 1 - SUV) | KK. Araojo | No | Public Bidding | 2023-05-03 | 2023-05-17 | 2023-05-25 |  | 2023-06-06 | 2023-06-06 | 2023-07-07 | 2023-07-07 | - | - | - | - | - | SBUI FY 2023 | 2500000 |  | 2500000 | - |  | - | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-18 |  | 2023-05-18 | 2023-05-18 | 2023-06-09 | -
5 | Procurement of Hardware and Glass Materials for Infrastructure and Smart Campus Development-Operationalization of Face-to-Face Classes (2nd Bidding) | BH. Nuyda | No | Public Bidding | N/A | 2023-05-17 | 2023-05-25 |  | 2023-06-06 | 2023-06-06 | 2023-06-14 | 2023-06-14 | 2023-06-20 | 2023-06-23 | - | - | - | GAA FY 2022 | 2456520.3 |  | 2456520.3 | 2338396 |  | 2338396 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-18 |  | 2023-05-18 | 2023-05-18 | 2023-06-09 | -
6 | Procurement of Supplies and Materials for Repair and Rehab of Various Buildings to Increase the Carrying Capacity of Nursing and Allied Health Programs (Lot 6 - Furniture & Fixtures) | BH. Nuyda | No | Public Bidding | 2023-05-17 | 2023-05-22 | 2023-05-30 |  | 2023-06-13 | 2023-06-13 | 2023-06-16 | 2023-06-16 | 2023-06-20 | 2023-06-22 | - | - | - | GAA FY 2022 | 338500 |  | 338500 | 337755 |  | 337755 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 | -
7 | Renewal of Student Information and Accounting System with Learning Management System (LMS) Subscription for One Year | ME. Abundo | No | Public Bidding | 2023-05-17 | 2023-05-25 | 2023-06-02 |  | 2023-06-14 | 2023-06-14 | 2023-06-21 | 2023-06-21 | 2023-06-27 | 2023-06-29 | 2023-07-12 | - | - | SBUI FY 2023 | 7000000 |  | 7000000 | 7000000 |  | 7000000 | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-26 |  | 2023-05-26 | 2023-05-26 | 2023-06-20 | -
[18 empty] | Total Alloted Budget of On-going Procurement Activities | 47689801.8 | 0 | 47689801.8 | 39186457.95 | 0 | 39186457.95
[18 empty] | Prepared by: |  |  |  |  | Recommended for Approval by: | [5 empty] | APPROVED:
[18 empty] | GERALDINE M.ARCILLA |  |  |  |  | LILY P. CUSTODIO, Ph.D. | [5 empty] | PATRICK ALAIN T. AZANZA, Ph.D.
[18 empty] | BAC Secretariat |  |  |  |  | BAC Chairperson | [5 empty] | SUC President III
3 | Procurement of Laboratory Equipment for Nutrition & Dietetics | J. Olfindo | No | Public Bidding | 2023-03-09 | 2023-03-10 | 2023-03-20 |  | 2023-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2022 | 547650 |  | 547650 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-03-06 |  | 2023-03-06 | 2023-03-06 | 2023-03-06 | - | Failure of Bidding: No bidder
4 | Supply, Delivery, Insallation, Testing and Commissioning of Standby Diesel Generator Set with Accessories | BH. Nuyda | No | Public Bidding | 2023-03-02 | 2023-05-09 | 2023-05-17 |  | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2022 | 2376296.9 |  | 2376296.9 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-10 |  | 2023-05-10 | 2023-05-10 | 2023-05-10 | - | Failure of Bidding: No bidder
5 | Procurement of Sports Utility Vehicle & Motorcycle (Lot 2 - Motorcycle) | KK. Araojo | No | Public Bidding | 2023-05-03 | 2023-05-17 | 2023-05-25 |  | 2023-06-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | SBUI FY 2023 | 150000 |  | 150000 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-18 |  | 2023-05-18 | 2023-05-18 | 2023-06-09 | - | Failure of Bidding: No bidder
6 | Procurement of Supplies and Materials for Repair and Rehab of Various Buildings to Increase the Carrying Capacity of Nursing and Allied Health Programs (Lots 1-5) | BH. Nuyda | No | Public Bidding | 2023-05-17 | 2023-05-22 | 2023-05-30 |  | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2022 | 10092318.05 |  | 10092318.05 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 | - | Failure of Bidding: No bidder
7 | Supply, Delivery, Installation, testing and Commissioning of Air-Conditioning Units for CatSU E-Library | BH. Nuyda | No | Public Bidding | 2023-05-17 | 2023-05-22 | 2023-05-30 |  | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2023 | 1223989.5 |  | 1223989.5 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 | - | Failure of Bidding: No bidder
8 | Procurement of Six (6) Months Janitorial Manpower Services | B. Abundo | No | Public Bidding | 2023-05-17 | 2023-05-24 | 2023-06-01 |  | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2023 | 2746827.33 |  | 2746827.33 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-05-26 |  | 2023-05-26 | 2023-05-26 | 2023-05-26 | - | Failure of Bidding: No bidder
14 | Procurement of Laboratory Equipment for Nutrition & Dietetics (2nd Bidding) | J. Olfindo | No | Public Bidding | NA | 2023-06-05 | 2023-06-14 |  | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2022 | 547650 |  | 547650 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-06-06 |  | 2023-06-06 | 2023-06-06 | 2023-06-06 | - | Failure of Bidding: No bidder
15 | Supply, Delivery, Insallation, Testing and Commissioning of Standby Diesel Generator Set with Accessories (2nd Bidding) | BH. Nuyda | No | Public Bidding | NA | 2023-06-05 | 2023-06-14 |  | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GAA FY 2022 | 2376296.9 |  | 2376296.9 | N/A |  | N/A | 1. Ms. Michelle Go 2. Mr. Franklin Boñales 3. Mr. Rundy P. Lizaso | 2023-06-06 |  | 2023-06-06 | 2023-06-06 | 2023-06-06 | - | Failure of Bidding: No bidder
What is completed proc activity?
- completely paid? With ntp? Ongoing construction/delivery?
- failed included? Failed at 1st or 2nd bidding
what is ongoing?
- from last year but ongoing delivery?
- failed but ongoing/continuing proc
how to present itemized or with lots (ok & failed)